## Test cases
Smoke TC ID | Testing Type | Module | Test Scenario | Test Steps | Expected Result | Actual Result | Status | Remarks
SMK-001 | Smoke | App Launch | Launch the app | Open the application | Application launches successfully | Application launched successfully | Pass | Smoke test passed
SMK-002 | Smoke | Home Screen | Verify Home screen loads | Navigate to Home screen | Home screen is displayed correctly | Displayed correctly | Pass | Working as expected
SMK-003 | Smoke | Video Link | Verify video link field is accessible | Tap on the video link field | User can enter a video URL | Field is editable | Pass | Working
SMK-004 | Smoke | Download | Verify Download button is clickable | Tap Download button after entering a valid URL | Download process starts successfully | Download initiated | Pass | Working
SMK-005 | Smoke | Storage Path | Verify storage path is displayed | View selected storage path | Storage path is visible | Displayed | Pass | Working
SMK-006 | Smoke | Navigation | Verify Home tab navigation | Tap Home tab | Home page opens successfully | Opened successfully | Pass | Working
SMK-007 | Smoke | Navigation | Verify Saved tab navigation | Tap Saved tab | Saved Videos page opens | Opened successfully | Pass | Working
SMK-008 | Smoke | Navigation | Verify Settings tab navigation | Tap Settings tab | Settings page opens | Opened successfully | Pass | Working
SMK-009 | Smoke | Saved Videos | Verify Saved Videos screen loads | Open Saved tab | Saved videos are displayed | Displayed successfully | Pass | Working
SMK-010 | Smoke | Settings | Verify Dark Mode toggle works | Enable/Disable Dark Mode | Dark Mode setting changes successfully | Working correctly | Pass | Working
SMK-011 | Smoke | Settings | Verify Auto-Download toggle works | Enable/Disable Auto-Download | Auto-Download setting updates | Working correctly | Pass | Working
SMK-015 | Smoke | Folder Selection | Verify folder selection works | Select a folder and confirm | Folder is selected successfully | Selected successfully | Pass | Working
TC ID | Testing Type | Module | Test Scenario | Test Steps | Expected Result | Actual Result | Status | Remarks
SMK-001 | Functional Testing | Video Link | Verify user can enter a valid video URL | Paste a valid video link in the input field | The video URL should be accepted successfully | URL accepted successfully | Pass | N/A
SMK-002 | Functional Testing | Video Link | Verify user can paste a copied video URL using the paste icon | Copy a valid URL and tap the paste icon | The copied URL should appear in the input field | URL pasted successfully | Pass | N/A
SMK-003 | Functional Testing | Video Link | Verify the application accepts Reel URLs | Enter a valid Reel URL | Reel URL should be accepted | URL accepted successfully | Pass | N/A
SMK-004 | Functional Testing | Video Link | Verify the application accepts Post URLs | Enter a valid Post URL | Post URL should be accepted | URL accepted successfully | Pass | N/A
SMK-005 | Functional Testing | Video Link | Verify the application rejects an invalid URL | Enter an invalid URL | The application should display an error message or prevent downloading | Error displayed successfully | Pass | N/A
SMK-007 | Functional Testing | Download Button | Verify the Download button downloads the video successfully | Enter a valid URL and tap Download | The video should download successfully | Video downloaded successfully | Pass | N/A
SMK-008 | Functional Testing | Download Button | Verify the Download button is disabled or restricted when no URL is entered | Tap Download without entering any URL | The download process should not start | Download restricted successfully | Pass | N/A
SMK-009 | Functional Testing | Download Button | Verify video downloads with an active internet connection | Download a valid video | Video should be downloaded successfully | Download successful | Pass | N/A
SMK-010 | Functional Testing | Download Button | Verify download behavior without an internet connection | Turn off the internet and tap Download | it starts playing saed vedios. | Error displayed successfully | Pass | N/A
SMK-011 | Functional Testing | Storage Path | Verify the selected storage path is displayed correctly | Open the Home page | The selected storage path should be visible | Displayed correctly | Pass | N/A
SMK-012 | Functional Testing | Storage Path | Verify the user can change the storage location | Tap on Selected Path and choose another folder | The selected folder should be updated successfully | Storage path updated successfully | Pass | N/A
SMK-013 | Functional Testing | Storage Path | Verify the downloaded video is saved in the selected folder | Download a video after selecting a folder | The video should be saved in the selected storage location | Video saved successfully | Pass | N/A
SMK-014 | Functional Testing | Storage Path | Verify the application handles folder permission restrictions | Select a restricted folder and download a video | The application should display an appropriate permission message | Permission message displayed | Pass | N/A
TC ID | Testing Type | Module | Test Scenario | Test Steps | Expected Result | Actual Result | Status | Remarks
SMK-015 | Functional Testing | Saved Videos | Verify downloaded videos appear in Saved Videos | Download a video and open Saved Videos | Downloaded video should be displayed in Saved Videos | Video displayed successfully | Pass | N/A
SMK-016 | Functional Testing | Saved Videos | Verify multiple downloaded videos are displayed | Download multiple videos | All downloaded videos should be displayed | All videos displayed successfully | Pass | N/A
SMK-017 | Functional Testing | Saved Videos | Verify user can play a saved video | Tap on a saved video | The selected video should play successfully | Video played successfully | Pass | N/A
SMK-018 | Functional Testing | Saved Videos | Verify Saved Videos page loads successfully | Open Saved tab | Saved Videos page should load without any issues | Page loaded successfully | Pass | N/A
SMK-019 | Functional Testing | Favorite Icon | Verify user can mark a video as favorite | Tap the heart icon | The selected video should be marked as favorite | Video marked as favorite successfully | Pass | N/A
SMK-020 | Functional Testing | Favorite Icon | Verify the heart icon changes when marked as favorite | Tap the heart icon | The heart icon should remain highlighted | Heart icon highlighted successfully | Pass | N/A
SMK-021 | Functional Testing | Favorite Icon | Verify favorite status is retained after navigating to another tab | Mark a video as favorite and navigate to Home tab then return | The favorite status should remain unchanged | Favorite status is removed after returning to Saved Videos | Fail | Favorite state is not persistent.
SMK-022 | Functional Testing | Favorite Icon | Verify favorite videos are stored separately | Mark a video as favorite | Favorite videos should be accessible from a dedicated Favorites section | No dedicated Favorites section is available in the application | Fail | Favorites management functionality is missing.
SMK-024 | Functional Testing | Saved Videos | Verify Saved Videos remain visible after reopening the application | Close and reopen the app | Previously downloaded videos should still be displayed | Videos are displayed successfully | Pass | N/A
TC ID | Testing Type | Module | Test Scenario | Test Steps | Expected Result | Actual Result | Status | Remarks
SMK-026 | Functional Testing | Notifications | Verify the Notifications page loads successfully | Open the Notifications page | Notifications page should open successfully without any errors | Notifications page opened successfully | Pass | N/A
SMK-027 | Functional Testing | Notifications | Verify the "No Notifications" message is displayed when no notifications are available | Open the Notifications page when no notifications are present | The "No Notifications" message should be displayed | Message displayed successfully | Pass | N/A
SMK-028 | Functional Testing | Notifications | Verify the description text is displayed correctly | Observe the description text | "You're all caught up! Check back later." should be displayed correctly | Text displayed correctly | Pass | N/A
SMK-029 | Functional Testing | Notifications | Verify the back button functionality | Tap the back button | User should be redirected to the previous screen | Redirected successfully | Pass | N/A
SMK-031 | Functional Testing | Notifications | Verify the delete icon functionality | Tap the delete icon | All notifications should be deleted | No notifications are available to perform this action | Pass | N/A
SMK-032 | Functional Testing | Notifications | Verify the page handles the empty state correctly | Open the page without any notifications | The application should not crash or display any UI issues | Empty state handled successfully | Pass | N/A
SMK-034 | Functional Testing | Notifications | Verify the "Mark as Read" icon marks all notifications as read | Generate one or more notifications and tap the tick (✓) icon | All unread notifications should be marked as read successfully | Notifications were marked as read successfully | Pass | N/A
TC ID | Testing Type | Module | Test Scenario | Test Steps | Expected Result | Actual Result | Status | Remarks
SMK-035 | Functional Testing | Notifications | Verify user can enable Notifications | Turn ON the Notifications toggle | Notifications should be enabled successfully | Notifications enabled successfully | Pass | N/A
SMK-036 | Functional Testing | Notifications | Verify Notifications preference persists after reopening the app | Turn ON Notifications and reopen the application | Notifications toggle should remain ON | Notifications toggle is automatically turned OFF after reopening the app | Fail | Toggle state is not persistent.
SMK-037 | Functional Testing | Notifications | Verify user can disable Notifications | Turn OFF the Notifications toggle | Notifications should be disabled successfully | Notifications disabled successfully | Pass | N/A
SMK-038 | Functional Testing | Dark Mode | Verify user can enable Dark Mode | Turn ON Dark Mode | Application theme should change successfully | Dark Mode enabled successfully | Pass | N/A
SMK-039 | Functional Testing | Dark Mode | Verify Dark Mode preference persists after reopening the app | Enable Dark Mode and reopen the application | Dark Mode should remain enabled | Dark Mode is automatically disabled after reopening the app | Fail | Theme preference is not being saved.
SMK-040 | Functional Testing | Dark Mode | Verify user can disable Dark Mode | Turn OFF Dark Mode | Dark Mode should be disabled successfully | Dark Mode disabled successfully | Pass | N/A
SMK-041 | Functional Testing | Auto Download | Verify user can enable Auto Download | Turn ON Auto Download | Auto Download should be enabled successfully | Auto Download enabled successfully | Pass | N/A
SMK-042 | Functional Testing | Auto Download | Verify Auto Download preference persists after reopening the app | Enable Auto Download and reopen the application | Auto Download should remain enabled | Auto Download is automatically disabled after reopening the app | Fail | Toggle state is not persistent.
SMK-043 | Functional Testing | Auto Download | Verify user can disable Auto Download | Turn OFF Auto Download | Auto Download should be disabled successfully | Auto Download disabled successfully | Pass | N/A
SMK-044 | Functional Testing | Manage Subscription | Verify Manage Subscription page opens successfully | Tap Manage Subscription | Subscription page should open successfully | Opened successfully | Pass | N/A
SMK-045 | Functional Testing | Privacy Policy | Verify Privacy Policy page opens successfully | Tap Privacy Policy | Privacy Policy page should open successfully | Opened successfully | Pass | N/A
SMK-046 | Functional Testing | Privacy Policy | Verify Privacy Policy content is displayed properly | Scroll through the page | All privacy policy content should be displayed without UI issues | Displayed successfully | Pass | N/A
SMK-047 | Functional Testing | Privacy Policy | Verify back button functionality | Tap the back button | User should return to the Settings page | Returned successfully | Pass | N/A
SMK-048 | Functional Testing | Terms and Conditions | Verify Terms and Conditions page opens successfully | Tap Terms and Conditions | Terms page should open successfully | Opened successfully | Pass | N/A
SMK-049 | Functional Testing | Terms and Conditions | Verify all terms are displayed properly | Scroll through the page | All terms should be displayed properly | Displayed successfully | Pass | N/A
SMK-050 | Functional Testing | Terms and Conditions | Verify back button functionality | Tap the back button | User should return to the Settings page | Returned successfully | Pass | N/A
SMK-051 | Functional Testing | Support | Verify Support page opens successfully | Tap Support | Support page should open successfully | Opened successfully | Pass | N/A
SMK-052 | Functional Testing | Support | Verify Email Support option works | Tap Email Support | Email application should open successfully | Email application opened successfully | Pass | N/A
SMK-053 | Functional Testing | Support | Verify Website option works | Tap Website | Official website should open successfully | Website opened successfully | Pass | N/A
SMK-054 | Functional Testing | Support | Verify FAQ section is displayed properly | Scroll through the FAQ section | All FAQs should be displayed properly | Displayed successfully | Pass | N/A
SMK-055 | Functional Testing | More Apps | Verify More Apps page opens successfully | Tap More Apps | More Apps section should open successfully | Opened successfully | Pass | N/A
SMK-056 | Functional Testing | Watch Rewarded Ad | Verify rewarded ad is displayed successfully | Tap Watch Rewarded Ad | Rewarded ad should be displayed successfully | Rewarded ad displayed successfully | Pass | N/A
SMK-057 | Functional Testing | Watch Rewarded Ad | Verify the user receives the reward after watching the rewarded ad | Watch the rewarded ad completely | The application should clearly indicate that the reward has been granted and display or apply it accordingly | No indication of any reward is displayed after watching the ad | Fail | Reward functionality is unclear and cannot be verified by the user.